## START
Preparation tracker | One workbook for the whole plan. Fill it in daily; it takes about 5 minutes.
How dates work | Change the START DATE below to the Monday you start. Every date in DAILY moves with it.
START DATE (a Monday) | 2026-10-26
DAILY | One row per day (224). Status: Not started / In progress / Done / Needs review / Deferred. 'Done' only when the day's 'Done when' is true.
DSA_LOG | Every planned problem, pre-filled. Fill Result, the date and the six fields. Re-solve dates calculate themselves (D+1, 3, 7, 14).
REVIEW | Every 'explain aloud' question, pre-filled. Enter the date you learned it; review dates calculate (D+1, 3, 7, 14, 30).
WEAK | Anything you could not explain or solve. Exit rule: two successful recalls at least 7 days apart.
DESIGNS | Every HLD and LLD with its planned day. Score yourself out of 20 with the practice rubric.
STORIES | Your real stories mapped to the 16 Amazon Leadership Principles. Never invent; leave unknown numbers blank.
JOURNAL | One line per working day: problem, decision, outcome. This becomes your story bank.
PROJECT | Milestones M1–M12 with acceptance tests.
APPLY / INTERVIEWS | Applications from Week 21; an analysis within 24 hours of every interview.
DASHBOARD | Counts that update themselves.

## DAILY
Day | Date | Weekday | Week | Phase | Focus | DSA problems | Core / rotating topic | Explain aloud | Status | Minutes | Recall | Week file | Notes
1 |  |  | 1 | Foundations | Array representation and traversal | Array basics: print, sum, max, min, count of a target (handle empty input) | C# program basics: a console project, variables and built-in types, arrays and Length | Why is reading a[i] O(1) but finding a value O(n)? | Not started
2 |  |  | 1 | Foundations | Indexes, linear search and operation costs | Linear search, first/last occurrence, minimum/maximum with index | int vs long, integer division, overflow, checked arithmetic and conversions | What is overflow and when should a sum use long? | Not started
3 |  |  | 1 | Foundations | Swapping and reversing in place | Reverse an array in place with two indexes (0, 1, odd, even lengths) | Methods, parameters, return values; value types vs reference types | What does a variable of a value type hold, and what does a reference-type variable hold? | Not started
4 |  |  | 1 | Foundations | Sorted check and second-largest distinct | Check sorted order; second-largest DISTINCT value | Stack vs heap, where structs actually live, null vs empty, alias vs copy | Where does a struct live — the stack or the heap? (It depends on where it is declared.) | Not started
5 |  |  | 1 | Foundations | Repair and retrieval | re-solves + Concatenation of Array | re-explain the week |  | Not started
6 |  |  | 1 | Foundations | Deep work: DSA + design + lab/project | Insert / delete at an index by shifting, with spare capacity, Contains Duplicate | How a web request works, on paper: client → DNS → server → API → database → response. Draw it. No scaling yet. |  | Not started
7 |  |  | 1 | Foundations | Weekly test, review, project, stories |  | Predict-then-run lab: write 6 small C# examples about assignment and parameters (int, struct, class, array, string, ref) |  | Not started
8 |  |  | 2 | Foundations | Set membership and duplicate detection | Contains Duplicate, Frequency map of an int[] with Dictionary (TryGetValue) | Struct vs class, boxing and its hidden cost, nullable value types | What is boxing, what does it cost, and name three places it happens by accident. | Not started
9 |  |  | 2 | Foundations | Two Sum, brute force first | Two Sum | Equality: ==, Equals, GetHashCode, IEquatable<T>, records | State the Equals/GetHashCode contract and what breaks without it. | Not started
10 |  |  | 2 | Foundations | Two Sum in one pass with a map | Two Sum, Longest Consecutive Sequence | List<T>, Dictionary and HashSet internals: growth, buckets, collisions | Why is Dictionary lookup O(1) on average, and what makes it O(n)? | Not started
11 |  |  | 2 | Foundations | Reader and writer pointers | Move Zeroes, Remove Element | ref, out, in; const vs readonly vs static; static constructors; object memory layout | Explain ref, out and in in one sentence each. | Not started
12 |  |  | 2 | Foundations | Repair and retrieval | re-solves + Find All Numbers Disappeared in an Array | re-explain the week |  | Not started
13 |  |  | 2 | Foundations | Deep work: DSA + design + lab/project | Remove Duplicates from Sorted Array, Running Sum of 1d Array, Plus One, Merge Sorted Array, Range Sum Query - Immutable | API contract on paper: POST /jobs and GET /jobs/{id} — inputs, validation, status codes, stored fields. No code. |  | Not started
14 |  |  | 2 | Foundations | Weekly test, review, project, stories |  | Re-solve Two Sum cold. Then explain Range Sum Query (303) from Saturday: derive prefix[r+1] − prefix[l] on paper, includ |  | Not started
15 |  |  | 3 | Foundations | String traversal and frequency | Valid Anagram, Ransom Note | Strings: immutability, interning, StringBuilder, why concatenation in a loop is O(n²) | Why is string concatenation in a loop O(n²)? | Not started
16 |  |  | 3 | Foundations | Opposite-end pointers | Valid Palindrome, Valid Palindrome II | Classes, constructors and chaining, fields vs properties, the six access modifiers | What is the job of a constructor? | Not started
17 |  |  | 3 | Foundations | Pointers on sorted input | Two Sum II - Input Array Is Sorted, Squares of a Sorted Array | virtual / override / new; interface vs abstract class | Interface or abstract class — how do you decide? | Not started
18 |  |  | 3 | Foundations | Fixed-size windows | Maximum Average Subarray I, Longest Common Prefix | Composition over inheritance; generics, constraints and variance; generics vs Java erasure | Why composition over inheritance? | Not started
19 |  |  | 3 | Foundations | Repair and retrieval | re-solves + Reverse String | re-explain the week |  | Not started
20 |  |  | 3 | Foundations | Deep work: DSA + design + lab/project | First Unique Character in a String, Isomorphic Strings, Word Pattern, 3Sum | URL shortener — requirements only: 3 functional requirements, 3 constraints, the redirect API. Single server. Read the c |  | Not started
21 |  |  | 3 | Foundations | Weekly test, review, project, stories |  | Implement IComparable<T> and IEquatable<T> on a Money record; sort a list of jobs by priority with a custom IComparer. |  | Not started
22 |  |  | 4 | Foundations | Window validity and shrink rules | Longest Substring Without Repeating Characters | IEnumerable vs ICollection vs IList vs IQueryable; what yield return compiles into | IEnumerable vs IQueryable — why does it matter for a database query? | Not started
23 |  |  | 4 | Foundations | Monotone windows and their limits | Minimum Size Subarray Sum, Max Consecutive Ones III | Deferred execution and LINQ costs | What is deferred execution and give one bug it causes. | Not started
24 |  |  | 4 | Foundations | Prefix sums plus a frequency map | Subarray Sum Equals K | Delegates, lambdas, closures and events | What does a closure allocate, and what is the loop-variable trap? | Not started
25 |  |  | 4 | Foundations | Local and global optimum (Kadane) | Best Time to Buy and Sell Stock, Maximum Subarray | Exceptions: throw vs throw ex, filters, cost, using and IDisposable basics | What is the difference between throw and throw ex? | Not started
26 |  |  | 4 | Foundations | Repair and retrieval | re-solves + Contains Duplicate II | re-explain the week |  | Not started
27 |  |  | 4 | Foundations | Deep work: DSA + design + lab/project | Product of Array Except Self, Longest Repeating Character Replacement, Permutation in String, Group Anagrams | URL shortener — data model and key generation (base62 counter vs hash), a cache, and a request-rate estimate. Still one |  | Not started
28 |  |  | 4 | Foundations | Month 1 checkpoint |  | Month 1 test (see checkpoint below). Then repair the weakest prerequisite you found. |  | Not started
29 |  |  | 5 | Foundations | Binary search invariant | Binary Search, Search Insert Position | IDisposable, using, the dispose pattern and finalizers | Why does a finalizer make collection take (at least) two GC cycles? | Not started
30 |  |  | 5 | Foundations | Lower and upper bounds | Find First and Last Position of Element in Sorted Array, First Bad Version | GC generations, the large object heap, workstation vs server GC | Why is a gen 0 collection cheap and a gen 2 collection expensive? | Not started
31 |  |  | 5 | Foundations | Rotated sorted arrays | Find Minimum in Rotated Sorted Array, Search in Rotated Sorted Array | async/await: what await does and the generated state machine | What does await actually do? | Not started
32 |  |  | 5 | Foundations | Binary search on the answer | Koko Eating Bananas, Capacity To Ship Packages Within D Days | async pitfalls: async void, .Result deadlock, ConfigureAwait, ValueTask, CancellationToken | Why does calling .Result deadlock in an app with a synchronization context? | Not started
33 |  |  | 5 | Foundations | Repair and retrieval | re-solves + Sqrt(x) | re-explain the week |  | Not started
34 |  |  | 5 | Foundations | Deep work: DSA + design + lab/project | Implement merge sort (stable, O(n log n), O(n) extra), Implement quicksort partition (Lomuto and Hoare) and quickselect, Sort an Array, Sort Colors | URL shortener — full 30-minute design: requirements, estimate, API, schema and indexes, cache, one failure (cache down). |  | Not started
35 |  |  | 5 | Foundations | Weekly test, review, project, stories |  | Read Stephen Toub's 'How Async/Await Really Works in C#' (devblogs.microsoft.com) for 60 minutes; write a six-question s |  | Not started
36 |  |  | 6 | Foundations | Linked-list reference mutation | Reverse Linked List, Middle of the Linked List | OS vocabulary; process vs thread vs Task; the thread pool and starvation | What is thread-pool starvation and how would you spot it? | Not started
37 |  |  | 6 | Foundations | Dummy node and merging | Merge Two Sorted Lists, Remove Nth Node From End of List | Race conditions, lock, Interlocked, volatile | What is a race condition at the memory level? | Not started
38 |  |  | 6 | Foundations | Cycles and palindromes | Linked List Cycle, Palindrome Linked List | Deadlock, why not await inside lock, SemaphoreSlim vs Mutex vs ReaderWriterLockSlim | What causes a deadlock and how do you prevent one? | Not started
39 |  |  | 6 | Foundations | Stack and queue contracts | Valid Parentheses, Implement Queue using Stacks | Channel<T>, Parallel.For/PLINQ; your email pipeline as a concurrency story | When does Parallel.For hurt rather than help? | Not started
40 |  |  | 6 | Foundations | Repair and retrieval | re-solves + Intersection of Two Linked Lists | re-explain the week |  | Not started
41 |  |  | 6 | Foundations | Deep work: DSA + design + lab/project | Min Stack, Evaluate Reverse Polish Notation, Reorder List, Add Two Numbers | LLD: logging framework — levels, sinks (console, file, in-memory), formatting, async buffering. Requirements → classes → |  | Not started
42 |  |  | 6 | Foundations | Weekly test, review, project, stories |  | Implement the logger from Saturday's design: console + in-memory sinks, levels, and tests. Add a new sink without changi |  | Not started
43 |  |  | 7 | Foundations | Recursion mechanics | Recursive sum, factorial, power, reverse a string — draw the call stack, Fibonacci three ways: naive recursion, memo, iterative — compare cost, Fibonacci Number | .NET Framework vs .NET Core vs modern .NET; CLR, SDK, BCL; JIT, tiered compilation, ReadyToRun, AOT | .NET Framework vs modern .NET in sixty seconds. | Not started
44 |  |  | 7 | Foundations | Choose, explore, unchoose | Subsets, Pow(x, n) | GC gen 0 vs gen 2, the LOH; trace a request from Kestrel to your endpoint and back | Trace a request from Kestrel to your controller and back. | Not started
45 |  |  | 7 | Foundations | Permutations | Permutations, Letter Combinations of a Phone Number | Middleware order (with the CORS correction) and DI lifetimes / captive dependencies | Explain DI lifetimes and the captive dependency problem. | Not started
46 |  |  | 7 | Foundations | Pruning and repeated candidates | Combination Sum, Generate Parentheses | Configuration precedence, IOptions, validation and ProblemDetails | How does configuration precedence work? | Not started
47 |  |  | 7 | Foundations | Repair and retrieval | re-solves + Combination Sum III | re-explain the week |  | Not started
48 |  |  | 7 | Foundations | Deep work: DSA + design + lab/project | Subsets II, Permutations II, Word Search, Palindrome Partitioning | LLD: parking lot — requirements, vehicle and spot types, allocation strategy, ticket and payment, state changes. Sequent |  | Not started
49 |  |  | 7 | Foundations | Weekly test, review, project, stories |  | Reproduce a captive dependency in the API (scoped DbContext-like service inside a singleton), see the bug, fix it with I |  | Not started
50 |  |  | 8 | Foundations | Tree recursion | Maximum Depth of Binary Tree, Invert Binary Tree, Same Tree | HTTP and REST: methods, idempotency, status codes, versioning | Which HTTP methods are idempotent, and why does it matter? | Not started
51 |  |  | 8 | Foundations | Level-order BFS | Binary Tree Level Order Traversal, Binary Tree Right Side View | JWT: structure, signing vs encryption, validation, revocation; authentication vs authorization | What is inside a JWT, and what is the difference between signing and encryption? | Not started
52 |  |  | 8 | Foundations | BST global invariant | Validate Binary Search Tree, Kth Smallest Element in a BST | EF Core change tracker, AsNoTracking, projections, N+1 | What is the N+1 problem, how do you find it, and how do you fix it? | Not started
53 |  |  | 8 | Foundations | Subtree combination and BST LCA | Diameter of Binary Tree, Balanced Binary Tree, Lowest Common Ancestor of a Binary Search Tree | Cache-aside vs write-through vs write-behind, stampede, BackgroundService | Compare cache-aside, write-through and write-behind. | Not started
54 |  |  | 8 | Foundations | Repair and retrieval | re-solves + Subtree of Another Tree | re-explain the week |  | Not started
55 |  |  | 8 | Foundations | Deep work: DSA + design + lab/project | Lowest Common Ancestor of a Binary Tree, Construct Binary Tree from Preorder and Inorder Traversal, Path Sum, Count Good Nodes in Binary Tree | FIRST DESIGN MOCK (45 minutes, timer on, talk aloud, ideally with a partner): URL shortener from a blank page. Score you |  | Not started
56 |  |  | 8 | Foundations | Month 2 checkpoint |  | Month 2 test (see checkpoint). Then repair the weakest item. |  | Not started
57 |  |  | 9 | Core depth and the project starts | Heap invariant and PriorityQueue | Kth Largest Element in an Array, Last Stone Weight | SQL basics and data modeling: keys, constraints, normalization, when to denormalise | When would you denormalise on purpose? | Not started
58 |  |  | 9 | Core depth and the project starts | Frequency plus top-K | Top K Frequent Elements, K Closest Points to Origin | How data is stored; indexes, write cost, covering indexes | Why does an index make reads faster and writes slower? | Not started
59 |  |  | 9 | Core depth and the project starts | K-way merging | Merge k Sorted Lists, Task Scheduler | Execution plans, seek vs scan vs lookup, SARGability, join algorithms | Why can WHERE YEAR(created) = 2026 not use an index? | Not started
60 |  |  | 9 | Core depth and the project starts | Two heaps and selection without full sort | Find Median from Data Stream, Implement quicksort partition (Lomuto and Hoare) and quickselect | Logical execution order, window functions, CTEs, connection pooling | What is the logical execution order of a SQL statement? | Not started
61 |  |  | 9 | Core depth and the project starts | Repair and retrieval | re-solves + Kth Largest Element in a Stream | re-explain the week |  | Not started
62 |  |  | 9 | Core depth and the project starts | Deep work: DSA + design + lab/project | Top K Frequent Words, Reorganize String, Sort Characters By Frequency, Implement a binary min-heap (push, pop, heapify) on an array | LLD: LRU cache — Dictionary + doubly linked list, O(1) get and put; then thread safety (one lock vs ReaderWriterLockSlim |  | Not started
63 |  |  | 9 | Core depth and the project starts | Weekly test, review, project, stories |  | Finish all 20 practice queries; check your answers; put any you missed on the WEAK sheet. Implement LRU Cache (146) from |  | Not started
64 |  |  | 10 | Core depth and the project starts | Graph representation and DFS | Number of Islands, Flood Fill | Transactions, ACID, anomalies, isolation levels | State the four ACID properties and what each protects. | Not started
65 |  |  | 10 | Core depth and the project starts | Graph identity and copying | Clone Graph, Max Area of Island | Write skew, snapshot isolation, MVCC vs locking | What is write skew, and why does snapshot isolation permit it? | Not started
66 |  |  | 10 | Core depth and the project starts | Multi-source BFS | Rotting Oranges, 01 Matrix | Locks, deadlocks, lock escalation, optimistic vs pessimistic concurrency | Optimistic or pessimistic locking — when each? | Not started
67 |  |  | 10 | Core depth and the project starts | Reachability with reversed reasoning | Pacific Atlantic Water Flow, Surrounded Regions | Safe migrations, CDC, backup and restore | How do you change a schema without downtime? | Not started
68 |  |  | 10 | Core depth and the project starts | Repair and retrieval | re-solves + Find if Path Exists in Graph | re-explain the week |  | Not started
69 |  |  | 10 | Core depth and the project starts | Deep work: DSA + design + lab/project | Word Ladder, Is Graph Bipartite?, Walls and Gates, Keys and Rooms | Distributed rate limiter HLD: fixed window vs sliding window vs token bucket; atomic updates in Redis; per-tenant keys; |  | Not started
70 |  |  | 10 | Core depth and the project starts | Weekly test, review, project, stories |  | Do a SQL Server dirty-read demo (READ UNCOMMITTED / NOLOCK) if you have SQL Server; note PostgreSQL can never show one. |  | Not started
71 |  |  | 11 | Core depth and the project starts | Directed cycles | Course Schedule | What happens when you type a URL; DNS resolution | What happens when you type a URL and press enter? (5-minute version) | Not started
72 |  |  | 11 | Core depth and the project starts | Topological ordering | Course Schedule II | TCP handshake, flow vs congestion control, head-of-line blocking, HTTP/2 and HTTP/3 | Flow control or congestion control — what is the difference? | Not started
73 |  |  | 11 | Core depth and the project starts | Disjoint set union | Implement DSU: find with path compression, union by rank/size, Redundant Connection, Number of Provinces | TLS, what HTTPS does not protect, CORS and preflight, WebSockets | Explain CORS and preflight (with the corrected middleware order). | Not started
74 |  |  | 11 | Core depth and the project starts | Connectivity by shared identity | Accounts Merge | OS: process vs thread, context switches, virtual memory | Why is a context switch expensive? | Not started
75 |  |  | 11 | Core depth and the project starts | Repair and retrieval | re-solves + Find Eventual Safe States | re-explain the week |  | Not started
76 |  |  | 11 | Core depth and the project starts | Deep work: DSA + design + lab/project | Alien Dictionary, Graph Valid Tree, Number of Connected Components in an Undirected Graph, Minimum Height Trees | Job platform HLD v1 (your project): requirements, acceptance vs completion latency, API, schema, durable state machine, |  | Not started
77 |  |  | 11 | Core depth and the project starts | Weekly test, review, project, stories |  | PROJECT M1 — finish and prove the acceptance test: restart the API and read the job back; integration test for an illega |  | Not started
78 |  |  | 12 | Core depth and the project starts | Weighted shortest path | Network Delay Time | OS scheduler vs .NET scheduler; mutex, semaphore, spinlock; async I/O without a thread | Why does async I/O not need a thread while waiting? | Not started
79 |  |  | 12 | Core depth and the project starts | Sort and merge intervals | Merge Intervals, Insert Interval | Delivery guarantees, exactly-once processing, visibility timeouts | Explain the delivery guarantees, and how you get exactly-once *processing*. | Not started
80 |  |  | 12 | Core depth and the project starts | Greedy interval scheduling | Non-overlapping Intervals, Minimum Number of Arrows to Burst Balloons, Meeting Rooms II | Retries with jitter, DLQ, SQS vs RabbitMQ vs Kafka | SQS, RabbitMQ or Kafka — how do you choose? | Not started
81 |  |  | 12 | Core depth and the project starts | Reachability with greedy state | Jump Game, Gas Station | Kafka partitions and ordering, backpressure, the outbox pattern; HttpClient lifetime | What is the outbox pattern and what problem does it solve? | Not started
82 |  |  | 12 | Core depth and the project starts | Repair and retrieval | re-solves + Path With Minimum Effort | re-explain the week |  | Not started
83 |  |  | 12 | Core depth and the project starts | Deep work: DSA + design + lab/project | Cheapest Flights Within K Stops, Min Cost to Connect All Points, Jump Game II, Partition Labels | Notification service HLD: channels and preferences, async delivery through queues, retries per channel, duplicate preven |  | Not started
84 |  |  | 12 | Core depth and the project starts | Month 3 checkpoint |  | Month 3 test (see checkpoint). Then finish PROJECT M2: stop the worker in the middle of a job and show the message is re |  | Not started
85 |  |  | 13 | Core depth and the project starts | From recursion to DP | Climbing Stairs, Min Cost Climbing Stairs | Replication, read-your-writes, quorum, split brain | Why can a read replica serve stale data, and how do you hide that from a user? | Not started
86 |  |  | 13 | Core depth and the project starts | Take or skip | House Robber, House Robber II, N-th Tribonacci Number | Consistent hashing, sharding, hot keys, CAP and PACELC, consistency models | What does CAP actually say, and what is the common misreading? | Not started
87 |  |  | 13 | Core depth and the project starts | Unbounded choices | Coin Change, Decode Ways | Redis, eviction (LRU/LFU/TTL), cache patterns, invalidation, stampede | Why is Redis being single-threaded a feature? | Not started
88 |  |  | 13 | Core depth and the project starts | Segmentation and subsequences | Word Break, Longest Increasing Subsequence | Scaling fundamentals: vertical vs horizontal, stateless, load balancers L4/L7, gateways, discovery, DNS load balancing, CDN | L4 vs L7 load balancer? | Not started
89 |  |  | 13 | Core depth and the project starts | Repair and retrieval | re-solves + Combination Sum IV | re-explain the week |  | Not started
90 |  |  | 13 | Core depth and the project starts | Deep work: DSA + design + lab/project | Maximum Product Subarray, Longest Palindromic Substring, Palindromic Substrings, Combination Sum IV | LLD: split-expense service (Splitwise) — users, groups, expenses, split types (equal, exact, percent), balances, simplif |  | Not started
91 |  |  | 13 | Core depth and the project starts | Weekly test, review, project, stories |  | Finish PROJECT M3 and write its decision record (why outbox, polling vs CDC, ordering). |  | Not started
92 |  |  | 14 | Core depth and the project starts | 0/1 decisions | 0/1 knapsack (classic) — derive state, then 1-D array looping backwards, Partition Equal Subset Sum, Subset sum (boolean DP) | SOLID: single responsibility and open/closed | Explain Single Responsibility without reciting the definition. | Not started
93 |  |  | 14 | Core depth and the project starts | Counting: combinations vs permutations | Coin Change II, Target Sum | Liskov, Interface Segregation, Dependency Inversion; when a pattern is over-engineering | Why is Dependency Inversion not the same as using a DI container? | Not started
94 |  |  | 14 | Core depth and the project starts | Grid paths | Unique Paths, Unique Paths II, Minimum Path Sum | Strategy vs switch, event-handler leaks, Decorator vs inheritance; the 23 GoF patterns | Decorator or inheritance? | Not started
95 |  |  | 14 | Core depth and the project starts | More knapsack shapes | Ones and Zeroes, Perfect Squares, Last Stone Weight II | Repository over EF Core, Singleton, anti-patterns, testability | Why is untestable code usually badly designed code? | Not started
96 |  |  | 14 | Core depth and the project starts | Repair and retrieval | re-solves + Triangle | re-explain the week |  | Not started
97 |  |  | 14 | Core depth and the project starts | Deep work: DSA + design + lab/project | Triangle, Maximal Square, Count Square Submatrices with All Ones, Coin Change | LLD: rate limiter with a controllable clock — token bucket class, per-client policy, TimeProvider/FakeTimeProvider in te |  | Not started
98 |  |  | 14 | Core depth and the project starts | Weekly test, review, project, stories |  | Finish PROJECT M4 tests. Write down exactly where the guarantee stops (external effects). |  | Not started
99 |  |  | 15 | Core depth and the project starts | Two-string state | Longest Common Subsequence | Authentication vs authorization; JWT validation and negative tests | Why is 'authenticated' not the same as 'authorized'? | Not started
100 |  |  | 15 | Core depth and the project starts | Edit operations | Edit Distance, Interleaving String | Object- and function-level authorization; tenant isolation (OWASP API1, API5) | How do you prove tenant isolation rather than assert it? | Not started
101 |  |  | 15 | Core depth and the project starts | Stock state machines | Best Time to Buy and Sell Stock II, Best Time to Buy and Sell Stock with Cooldown | Input validation, injection, mass assignment, request limits, sensitive data in logs | What is mass assignment and how do DTOs prevent it? | Not started
102 |  |  | 15 | Core depth and the project starts | Subsequence families | Longest Palindromic Subsequence, Number of Longest Increasing Subsequence | CORS vs CSRF, SSRF, secrets management, threat modeling | Why is CORS not a CSRF defence? | Not started
103 |  |  | 15 | Core depth and the project starts | Repair and retrieval | re-solves + Distinct Subsequences | re-explain the week |  | Not started
104 |  |  | 15 | Core depth and the project starts | Deep work: DSA + design + lab/project | Distinct Subsequences, Word Break, Longest Increasing Subsequence, Decode Ways | LLD: elevator system — requests, direction, a state machine (Idle, MovingUp, MovingDown, DoorsOpen), a scheduling strate |  | Not started
105 |  |  | 15 | Core depth and the project starts | Weekly test, review, project, stories |  | Finish PROJECT M5. Run the tests from a clean checkout. |  | Not started
106 |  |  | 16 | Core depth and the project starts | Monotonic stack | Daily Temperatures, Next Greater Element I, Next Greater Element II | Docker: images, containers, layers, multi-stage builds | Why do multi-stage Docker builds matter? | Not started
107 |  |  | 16 | Core depth and the project starts | Monotonic deque and histogram | Sliding Window Maximum, Largest Rectangle in Histogram, Online Stock Span | Docker Compose (networks, volumes, health checks) and Linux basics | Why is 'localhost' inside a container not your machine? | Not started
108 |  |  | 16 | Core depth and the project starts | Tries | Implement Trie (Prefix Tree), Design Add and Search Words Data Structure, Search Suggestions System | Git workflow and CI: build, test, format, what each stage protects | What does your CI pipeline protect against, stage by stage? | Not started
109 |  |  | 16 | Core depth and the project starts | Bits | Single Number, Number of 1 Bits, Counting Bits, Missing Number, Reverse Bits | CD: environments, readiness vs liveness, safe migrations, rollback | Liveness or readiness — what is the difference and why does it matter? | Not started
110 |  |  | 16 | Core depth and the project starts | Repair and retrieval | re-solves + Remove K Digits | re-explain the week |  | Not started
111 |  |  | 16 | Core depth and the project starts | Deep work: DSA + design + lab/project | Trapping Rain Water, Word Search II, Sum of Two Integers, Single Number III | LLD: seat reservation (BookMyShow) — shows, seats, a 10-minute hold, concurrent requests for the same seat, payment time |  | Not started
112 |  |  | 16 | Core depth and the project starts | Month 4 checkpoint |  | Month 4 test (see checkpoint). Then a 5-minute project walkthrough recorded on video or audio. |  | Not started
113 |  |  | 17 | Project completion and design depth (Wee | Mixed array and window selection | Minimum Window Substring, Find All Anagrams in a String | Failure models, partitions, split brain, 2PC, Raft leader election | Why is two-phase commit avoided across services? | Not started
114 |  |  | 17 | Project completion and design depth (Wee | Mixed graph and tree selection | Copy List with Random Pointer, Shortest Path in Binary Matrix | Distributed locks, leases, fencing tokens, clocks (Lamport, vector, skew, monotonic) | Why can a distributed lock not be made safe with timeouts alone? | Not started
115 |  |  | 17 | Project completion and design depth (Wee | DP state repair | Number of Longest Increasing Subsequence, Longest Common Subsequence | The dual-write problem, sagas (choreography vs orchestration), compensation | Choreography or orchestration for a saga? | Not started
116 |  |  | 17 | Project completion and design depth (Wee | Changed constraints | Kth Largest Element in a Stream, Find Median from Data Stream | Circuit breakers, bulkheads, retry storms, backoff with jitter, load shedding, admission control | Explain circuit-breaker states and why retries alone amplify an outage. | Not started
117 |  |  | 17 | Project completion and design depth (Wee | Repair and retrieval | re-solves + Fruit Into Baskets | re-explain the week |  | Not started
118 |  |  | 17 | Project completion and design depth (Wee | Deep work: DSA + design + lab/project | Rotate Image, Spiral Matrix, Set Matrix Zeroes, Valid Sudoku | Chat (WhatsApp/Slack) HLD: connections and gateways, message ordering per conversation, offline delivery, presence, grou |  | Not started
119 |  |  | 17 | Project completion and design depth (Wee | Weekly test, review, project, stories |  | Write the failure-modes table for the project from what you OBSERVED (not what you expect). |  | Not started
120 |  |  | 18 | Project completion and design depth (Wee | Coding mock one | Time Based Key-Value Store, Find Peak Element | Logs, metrics, traces; RED/USE; correlation IDs; OpenTelemetry in .NET | What are RED and USE? | Not started
121 |  |  | 18 | Project completion and design depth (Wee | Mock repair | Search a 2D Matrix II, Kth Smallest Element in a Sorted Matrix | SLIs, SLOs, error budgets; p50/p95/p99 | What do p50, p95 and p99 tell you, and why not the average? | Not started
122 |  |  | 18 | Project completion and design depth (Wee | Coding mock two | Binary Tree Zigzag Level Order Traversal, Populating Next Right Pointers in Each Node | Cloud basics on AWS (compute, RDS, Amazon MQ/SQS, S3, IAM, VPC, cost); Kubernetes overview | What does least privilege mean in IAM? | Not started
123 |  |  | 18 | Project completion and design depth (Wee | Code comprehension | Sum Root to Leaf Numbers | Finding bottlenecks under load; tenant fairness | How do you stop one tenant starving the others? | Not started
124 |  |  | 18 | Project completion and design depth (Wee | Repair and retrieval | re-solves + Flatten Binary Tree to Linked List | re-explain the week |  | Not started
125 |  |  | 18 | Project completion and design depth (Wee | Deep work: DSA + design + lab/project | Reverse Nodes in k-Group, Kth Smallest Element in a BST, Path Sum II | News feed HLD: fan-out on write vs read, the celebrity problem, ranking, cursor pagination, caching. |  | Not started
126 |  |  | 18 | Project completion and design depth (Wee | Weekly test, review, project, stories |  | Trace one job end to end and screenshot it for the README. Tear down any cloud resources you do not need. |  | Not started
127 |  |  | 19 | Project completion and design depth (Wee | Binary-search follow-ups | Capacity To Ship Packages Within D Days, Split Array Largest Sum | Load testing with k6: open vs closed models, offered load vs throughput, acceptance vs completion | Why separate job acceptance latency from job completion time? | Not started
128 |  |  | 19 | Project completion and design depth (Wee | Tree follow-ups | Serialize and Deserialize Binary Tree, Binary Tree Maximum Path Sum | Diagnostics: dotnet-counters, traces, dumps; incident diagnosis from evidence | A latency spike with low CPU — what do you check first? | Not started
129 |  |  | 19 | Project completion and design depth (Wee | Graph follow-ups | Swim in Rising Water, Evaluate Division | Backup and restore, RPO/RTO, rollback; runbooks | What are RPO and RTO? | Not started
130 |  |  | 19 | Project completion and design depth (Wee | Mixed checkpoint | Longest Increasing Path in a Matrix, Path With Minimum Effort | Project defense: why a queue, worker death, bottleneck, unhandled failure | Walk me through exactly what happens when a worker dies mid-job. | Not started
131 |  |  | 19 | Project completion and design depth (Wee | Repair and retrieval | re-solves + Minimum Height Trees | re-explain the week |  | Not started
132 |  |  | 19 | Project completion and design depth (Wee | Deep work: DSA + design + lab/project | Critical Connections in a Network, Find the City With the Smallest Number of Neighbors at a Threshold Distance, Implement Bellman-Ford with negative-cycle detection, Longest Increasing Path in a Matrix | Ticket / hotel booking HLD: inventory invariant, holds with expiry, payment timeout and reconciliation, no double bookin |  | Not started
133 |  |  | 19 | Project completion and design depth (Wee | Weekly test, review, project, stories |  | Finish the benchmark report; mark every number with how it was measured. |  | Not started
134 |  |  | 20 | Project completion and design depth (Wee | Independent coding round | Asteroid Collision, Car Fleet | The design framework: the nine steps, the 45-minute budget, estimation numbers | What are the design steps, in order? | Not started
135 |  |  | 20 | Project completion and design depth (Wee | Repair the highest-impact weakness | Decode String, Basic Calculator II | The classic designs and the one hard part of each | Why are payment systems obsessed with idempotency? | Not started
136 |  |  | 20 | Project completion and design depth (Wee | Two shorter tasks | Insert Delete GetRandom O(1), Subarray Product Less Than K | Behavioral structure: STAR, 'I' vs 'we', Have Backbone, Earn Trust | Why does saying 'we' cost you the answer? | Not started
137 |  |  | 20 | Project completion and design depth (Wee | Code review and extension | Continuous Subarray Sum, Contiguous Array | Behavioral follow-ups; quantifying honestly; the flagship story; resume truth check | How do you answer 'what would you do differently?' | Not started
138 |  |  | 20 | Project completion and design depth (Wee | Repair and retrieval | re-solves + First Missing Positive | re-explain the week |  | Not started
139 |  |  | 20 | Project completion and design depth (Wee | Deep work: DSA + design + lab/project | Next Permutation, Find the Duplicate Number, Majority Element, Rotate Array | E-commerce checkout and inventory HLD (no overselling), then payment workflow HLD (idempotency keys, webhooks, reconcili |  | Not started
140 |  |  | 20 | Project completion and design depth (Wee | Week 20 gate (Month 5) |  | WEEK 20 GATE (see checkpoint). If several items are 'no', spend Weeks 21–22 repairing them before applying anywhere you |  | Not started
141 |  |  | 21 | Interview launch (Week 24 six-month asse | Coding-round delivery | Linked List Cycle II, Happy Number | Coding-round script: the first five minutes, thinking aloud, getting unstuck, taking hints | What do you do in the first five minutes of a coding round? | Not started
142 |  |  | 21 | Interview launch (Week 24 six-month asse | LLD drill | Odd Even Linked List, Intersection of Two Linked Lists | LLD drill (40 minutes): vending machine — states, coins, inventory, refunds | How do you approach a 45-minute LLD from a blank page? | Not started
143 |  |  | 21 | Interview launch (Week 24 six-month asse | Design drill | Minimum Remove to Make Valid Parentheses, Delete Node in a BST | Design drill (40 minutes): web crawler — frontier, politeness, dedup, distribution | How do you open a system design round? | Not started
144 |  |  | 21 | Interview launch (Week 24 six-month asse | Applications and recruiters | Open the Lock, Snakes and Ladders | Applications: target list, referrals, recruiter questions, why mid-tier first | Why apply to mid-tier companies first? | Not started
145 |  |  | 21 | Interview launch (Week 24 six-month asse | Repair and retrieval | re-solves + Last Stone Weight | re-explain the week |  | Not started
146 |  |  | 21 | Interview launch (Week 24 six-month asse | Deep work: DSA + design + lab/project | Stock Price Fluctuation, Snapshot Array | 45-minute design mock on a practised anchor (URL shortener or notification) with a changed requirement. |  | Not started
147 |  |  | 21 | Interview launch (Week 24 six-month asse | Weekly test, review, project, stories |  | Weekly review: classify this week's failures; plan next week's repairs. |  | Not started
148 |  |  | 22 | Interview launch (Week 24 six-month asse | No-IDE coding | Count Good Nodes in Binary Tree, Subtree of Another Tree | Coding without autocomplete; 'make it faster'; stating complexity | How do you code with no autocomplete and no compiler? | Not started
149 |  |  | 22 | Interview launch (Week 24 six-month asse | LLD drill | Course Schedule, Course Schedule II | LLD drill: task scheduler — priorities, delays, recurring tasks, worker threads | Where does concurrency appear in a task scheduler? | Not started
150 |  |  | 22 | Interview launch (Week 24 six-month asse | Design drill | Top K Frequent Elements, Top K Frequent Words | Design drills: YouTube (upload, transcoding, streaming) and typeahead (trie service, ranking, caching) | What separates a passing design from a strong one? | Not started
151 |  |  | 22 | Interview launch (Week 24 six-month asse | Communication under pressure | Partition Equal Subset Sum, Target Sum | When English stalls, answer length, recovering a bad answer, questions to ask; aptitude only if a target test needs it | Your English stalls mid-answer. What do you do? | Not started
152 |  |  | 22 | Interview launch (Week 24 six-month asse | Repair and retrieval | re-solves + Find if Path Exists in Graph | re-explain the week |  | Not started
153 |  |  | 22 | Interview launch (Week 24 six-month asse | Deep work: DSA + design + lab/project | Min Cost to Connect All Points, Cheapest Flights Within K Stops | LLD mock: rate limiter or parking lot with a change request. |  | Not started
154 |  |  | 22 | Interview launch (Week 24 six-month asse | Weekly test, review, project, stories |  | Weekly review and application follow-ups. |  | Not started
155 |  |  | 23 | Interview launch (Week 24 six-month asse | Leadership Principles mapping | Reorder Data in Log Files, Most Common Word | All 16 Leadership Principles in plain words; map your stories | What is the Bar Raiser looking for? | Not started
156 |  |  | 23 | Interview launch (Week 24 six-month asse | Timed LLD one | Number of Islands, Rotting Oranges | Timed LLD: ATM (40 minutes, working C#) | Which states does an ATM have? | Not started
157 |  |  | 23 | Interview launch (Week 24 six-month asse | Amazon-leaning coding | LRU Cache, Merge Intervals | Timed LLD: library management system (40 minutes) | How do you keep an LLD extensible? | Not started
158 |  |  | 23 | Interview launch (Week 24 six-month asse | OA-style sketch | Word Ladder, K Closest Points to Origin | Package tracking in 20 minutes (OA-style), then post-interview analysis practice | How do you analyse an interview afterwards? | Not started
159 |  |  | 23 | Interview launch (Week 24 six-month asse | Repair and retrieval | re-solves + Integer to English Words | re-explain the week |  | Not started
160 |  |  | 23 | Interview launch (Week 24 six-month asse | Deep work: DSA + design + lab/project | Trapping Rain Water, Find Median from Data Stream | Amazon-style LLD mock (with LP questions mixed in). |  | Not started
161 |  |  | 23 | Interview launch (Week 24 six-month asse | Weekly test, review, project, stories |  | Weekly review; applications by verified priority. |  | Not started
162 |  |  | 24 | Interview launch (Week 24 six-month asse | No-IDE graphs and DP | Longest Increasing Path in a Matrix, Longest Common Subsequence | Hiring committee: how to be easy to write down | What does the hiring committee mean for how you answer? | Not started
163 |  |  | 24 | Interview launch (Week 24 six-month asse | Code comprehension | Evaluate Division, Minimum Height Trees | Code comprehension: read 45 minutes of open-source C#, explain it aloud, find a risk | What is the code comprehension round and how do you prepare? | Not started
164 |  |  | 24 | Interview launch (Week 24 six-month asse | Design: collaborative editing | Edit Distance, Longest Palindromic Substring | Google Docs design: OT vs CRDT, presence, conflict handling | How do two people edit the same paragraph safely? | Not started
165 |  |  | 24 | Interview launch (Week 24 six-month asse | Design: distributed cache | LFU Cache, LRU Cache | Distributed cache design: consistent hashing, replication, eviction, hot keys | How do you handle a hot key in a distributed cache? | Not started
166 |  |  | 24 | Interview launch (Week 24 six-month asse | Repair and retrieval | re-solves + Median of Two Sorted Arrays | re-explain the week |  | Not started
167 |  |  | 24 | Interview launch (Week 24 six-month asse | Deep work: DSA + design + lab/project | Word Search II, Largest Rectangle in Histogram | Full design mock (job platform, booking or notification). |  | Not started
168 |  |  | 24 | Interview launch (Week 24 six-month asse | Week 24 — six-month core assessment |  | SIX-MONTH ASSESSMENT (see checkpoint). |  | Not started
169 |  |  | 25 | Advanced depth, conversion and continuat | Weak-family repair | Minimum Window Substring, Longest Substring Without Repeating Characters | Kafka: when it beats SQS, consumer-group rebalancing, ordering | When does Kafka beat SQS, concretely? | Not started
170 |  |  | 25 | Advanced depth, conversion and continuat | Advanced strings (extension) | Find the Index of the First Occurrence in a String, KMP prefix function (LPS) by hand, then code | Log compaction, ISR and acks, exactly-once semantics; commits, poison messages | Kafka claims exactly-once semantics. Is that a contradiction? | Not started
171 |  |  | 25 | Advanced depth, conversion and continuat | Greedy vs DP | Coin Change, Jump Game | Stream processing: event time vs processing time, watermarks, windows | What is a watermark? | Not started
172 |  |  | 25 | Advanced depth, conversion and continuat | Timed maintenance | Repeated String Match, Longest Happy Prefix | Approximate counting, backfill and replay; schema evolution and Schema Registry | Why is replay a design requirement? | Not started
173 |  |  | 25 | Advanced depth, conversion and continuat | Repair and retrieval | re-solves + Shortest Palindrome | re-explain the week |  | Not started
174 |  |  | 25 | Advanced depth, conversion and continuat | Deep work: DSA + design + lab/project | Is Graph Bipartite?, Implement Bellman-Ford with negative-cycle detection | Ad-click aggregation HLD: event ingestion, dedup, windowed counts, late events, reconciliation with a batch job. |  | Not started
175 |  |  | 25 | Advanced depth, conversion and continuat | Weekly test, review, project, stories |  | Message-compatibility test in the project (old message, new worker). |  | Not started
176 |  |  | 26 | Advanced depth, conversion and continuat | Timed coding round | Maximal Square, Count Square Submatrices with All Ones | Linearizability vs serializability; snapshot isolation; read-your-writes and monotonic reads | Linearizability or serializability — what is the difference? | Not started
177 |  |  | 26 | Advanced depth, conversion and continuat | Range queries (extension) | Range Sum Query - Mutable, Segment tree with lazy propagation (range add, range sum) | Active-active vs active-passive; RPO and RTO; replication lag | Active-active or active-passive? | Not started
178 |  |  | 26 | Advanced depth, conversion and continuat | DP follow-up | Edit Distance, Longest Palindromic Subsequence | Time series and geospatial: cardinality, downsampling, geohash/quadtree, erasure coding | Why is cardinality the hard part of a metrics system? | Not started
179 |  |  | 26 | Advanced depth, conversion and continuat | Debugging under time pressure | Count of Smaller Numbers After Self, My Calendar I | Recovery drill: backup restore and regional failover on paper | How would you fail over your project to another region? | Not started
180 |  |  | 26 | Advanced depth, conversion and continuat | Repair and retrieval | re-solves + Smallest Range Covering Elements from K Lists | re-explain the week |  | Not started
181 |  |  | 26 | Advanced depth, conversion and continuat | Deep work: DSA + design + lab/project | Find Median from Data Stream, Merge k Sorted Lists | Metrics and monitoring system HLD; then evolve the URL shortener (or your project) to two regions. |  | Not started
182 |  |  | 26 | Advanced depth, conversion and continuat | Weekly test, review, project, stories |  | Recovery drill for the project (restore + failover on paper). |  | Not started
183 |  |  | 27 | Advanced depth, conversion and continuat | Mixed maintenance | Number of Islands, Kth Largest Element in an Array | AI-assisted development and LLM basics for a backend engineer | How do you use AI tools, and how do you verify their output? | Not started
184 |  |  | 27 | Advanced depth, conversion and continuat | Weakness transfer test | Search Suggestions System, Design Add and Search Words Data Structure | RAG: the pipeline stage by stage; why chunking matters | What is actually hard about building a RAG service? | Not started
185 |  |  | 27 | Advanced depth, conversion and continuat | Prefix problems | Word Search II, Maximum XOR of Two Numbers in an Array | Embeddings, similarity, vector indexes, pgvector | Why pgvector rather than a dedicated vector database? | Not started
186 |  |  | 27 | Advanced depth, conversion and continuat | Mock with real tools | Longest Increasing Path in a Matrix, Longest Consecutive Sequence | Hybrid search (BM25 + vector, RRF), reranking, evaluation | How do you evaluate a RAG system? | Not started
187 |  |  | 27 | Advanced depth, conversion and continuat | Repair and retrieval | re-solves + Critical Connections in a Network | re-explain the week |  | Not started
188 |  |  | 27 | Advanced depth, conversion and continuat | Deep work: DSA + design + lab/project | Course Schedule, Word Break | Proximity service (Yelp/nearby) and Uber matching HLDs: geohash/quadtree, location updates, matching. |  | Not started
189 |  |  | 27 | Advanced depth, conversion and continuat | Weekly test, review, project, stories |  | Write up the retrieval experiment: what changed, what improved, what failed. |  | Not started
190 |  |  | 28 | Advanced depth, conversion and continuat | Coding mock one | Largest Rectangle in Histogram, Trapping Rain Water | Grounded answers, citations, abstention; retrieval vs generation failures | Why must a RAG system be able to say 'I don't know'? | Not started
191 |  |  | 28 | Advanced depth, conversion and continuat | Repair one repeated bug | Reverse Nodes in k-Group, Sliding Window Maximum | Prompt injection, tenant access, document permissions | How do you stop a malicious document from making the model do something? | Not started
192 |  |  | 28 | Advanced depth, conversion and continuat | Coding mock two | Binary Tree Maximum Path Sum, Serialize and Deserialize Binary Tree | MCP: host/client/server, tools/resources/prompts, transports, security | Tools, resources and prompts in MCP — who controls each? | Not started
193 |  |  | 28 | Advanced depth, conversion and continuat | Code review exercise | LFU Cache, LRU Cache | AI operations: latency, cost, observability, model/index changes | How do you control the cost of an LLM feature? | Not started
194 |  |  | 28 | Advanced depth, conversion and continuat | Repair and retrieval | re-solves + Burst Balloons | re-explain the week |  | Not started
195 |  |  | 28 | Advanced depth, conversion and continuat | Deep work: DSA + design + lab/project | Partition to K Equal Sum Subsets, Shortest Path Visiting All Nodes | Object storage (S3-like) and file storage/sync (Dropbox) HLDs: metadata vs data, chunking, durability, erasure coding. |  | Not started
196 |  |  | 28 | Advanced depth, conversion and continuat | Month 7 checkpoint |  | Month 7 test (see checkpoint). |  | Not started
197 |  |  | 29 | Advanced depth, conversion and continuat | Re-solve failed problems | First Missing Positive, Find the Duplicate Number | Choose the extension: Kubernetes/KEDA or deep .NET diagnostics (by target role) | Why did you choose this extension for your target roles? | Not started
198 |  |  | 29 | Advanced depth, conversion and continuat | Pattern sheet | Container With Most Water, 3Sum | Extension lab, part 1 | Explain the extension in 2 minutes. | Not started
199 |  |  | 29 | Advanced depth, conversion and continuat | Algorithm breadth overview | Strongly connected components: Kosaraju and Tarjan, Implement Floyd-Warshall (all pairs) | Search, location and storage breadth | When would you use a trie service vs a search engine? | Not started
200 |  |  | 29 | Advanced depth, conversion and continuat | Remaining patterns | Merge Intervals, Non-overlapping Intervals | Remaining patterns: Interpreter and the rest of GoF; CQRS, event sourcing, DDD basics | When is CQRS over-engineering? | Not started
201 |  |  | 29 | Advanced depth, conversion and continuat | Repair and retrieval | re-solves + | re-explain the week |  | Not started
202 |  |  | 29 | Advanced depth, conversion and continuat | Deep work: DSA + design + lab/project | Maximal Rectangle, Matrix chain multiplication (interval DP) | Redo SD1–SD3 (URL shortener, rate limiter, notification) from a blank page; compare with your Month 3 notes. |  | Not started
203 |  |  | 29 | Advanced depth, conversion and continuat | Weekly test, review, project, stories |  | Update the README and resume only with what you built and measured. |  | Not started
204 |  |  | 30 | Advanced depth, conversion and continuat | Coding round one | Median of Two Sorted Arrays, Split Array Largest Sum | Oral monologue: C# and .NET (45 minutes, recorded) | Explain the .NET request pipeline end to end. | Not started
205 |  |  | 30 | Advanced depth, conversion and continuat | Repair round one | Count of Smaller Numbers After Self, Sliding Window Maximum | Oral monologue: databases | Explain isolation levels per engine. | Not started
206 |  |  | 30 | Advanced depth, conversion and continuat | Coding round two | Critical Connections in a Network, Swim in Rising Water | Oral monologue: networking and OS | What happens when you type a URL? | Not started
207 |  |  | 30 | Advanced depth, conversion and continuat | Experience and debugging round | Insert Delete GetRandom O(1), Time Based Key-Value Store | Oral monologue: distributed systems; resume and application refresh | Explain at-least-once delivery and idempotency. | Not started
208 |  |  | 30 | Advanced depth, conversion and continuat | Repair and retrieval | re-solves + | re-explain the week |  | Not started
209 |  |  | 30 | Advanced depth, conversion and continuat | Deep work: DSA + design + lab/project | Minimum Window Substring, Longest Valid Parentheses | 45-minute design mock with a partner, then redo two weak designs. |  | Not started
210 |  |  | 30 | Advanced depth, conversion and continuat | Weekly test, review, project, stories |  | Write the top three gaps and their repair tasks for Week 31. |  | Not started
211 |  |  | 31 | Advanced depth, conversion and continuat | Least-practised family | Clone Graph, Accounts Merge | Role-specific technical review for your active interviews | What will this company's loop test, according to the recruiter? | Not started
212 |  |  | 31 | Advanced depth, conversion and continuat | Interview feedback repair | LRU Cache, Find Median from Data Stream | Application follow-up and scheduling | How do you analyse an interview afterwards? | Not started
213 |  |  | 31 | Advanced depth, conversion and continuat | Follow-up adaptation | Top K Frequent Elements, Kth Largest Element in a Stream | Offer literacy: compensation, levels, negotiation basics | What do you say when asked for your expected salary? | Not started
214 |  |  | 31 | Advanced depth, conversion and continuat | Timed confidence check | Merge Intervals, Number of Islands | Relocation — only if still relevant (verify routes first) | Why do you want to move to this country? (only if relevant) | Not started
215 |  |  | 31 | Advanced depth, conversion and continuat | Repair and retrieval | re-solves + | re-explain the week |  | Not started
216 |  |  | 31 | Advanced depth, conversion and continuat | Deep work: DSA + design + lab/project | Binary Tree Maximum Path Sum, Edit Distance | Redo three designs with changed requirements. |  | Not started
217 |  |  | 31 | Advanced depth, conversion and continuat | Weekly test, review, project, stories |  | Weekly review of interviews and applications. |  | Not started
218 |  |  | 32 | Advanced depth, conversion and continuat | Core recall check | Two Sum, Reverse Linked List | C#/.NET/SQL recap with the rapid revision sheet | What is boxing and when does it happen? | Not started
219 |  |  | 32 | Advanced depth, conversion and continuat | Independent mixed assessment | Subarray Sum Equals K, Binary Tree Level Order Traversal | Negotiation preparation: level first, timelines, offers in writing | How do you ask for more time to decide? | Not started
220 |  |  | 32 | Advanced depth, conversion and continuat | Final repair | Coin Change, Course Schedule | Reliability, security and AI recap | How does your project behave when the database is down? | Not started
221 |  |  | 32 | Advanced depth, conversion and continuat | Continue from evidence | LRU Cache, Longest Substring Without Repeating Characters | Portfolio and career check; continuation plan | What did these eight months change in how you engineer? | Not started
222 |  |  | 32 | Advanced depth, conversion and continuat | Repair and retrieval | re-solves + | re-explain the week |  | Not started
223 |  |  | 32 | Advanced depth, conversion and continuat | Deep work: DSA + design + lab/project |  | Final design mock on a random anchor design. |  | Not started
224 |  |  | 32 | Advanced depth, conversion and continuat | Week 32 — final checkpoint |  | Month 8 final test (see checkpoint). |  | Not started

## DSA_LOG
Planned day | Problem | Difficulty | Pattern | Result | Solved on | Brute force | Insight (one sentence) | Invariant | Time / space | One variation | Re-solve D+1 | D+3 | D+7 | D+14 | Re-solve results
1 |  | Custom | Arrays | Not started
2 |  | Custom | Arrays | Not started
3 |  | Custom | Arrays | Not started
4 |  | Custom | Arrays | Not started
5 |  | Easy | Arrays | Not started
5 |  | Medium | Hashing | Not started
6 |  | Easy | Hashing | Not started
6 |  | Custom | Arrays | Not started
8 |  | Custom | Hashing | Not started
9 |  | Easy | Hashing | Not started
10 |  | Medium | Hashing | Not started
11 |  | Easy | Two pointers | Not started
11 |  | Easy | Two pointers | Not started
12 |  | Medium | Prefix sum | Not started
12 |  | Easy | Arrays | Not started
13 |  | Easy | Prefix sum | Not started
13 |  | Easy | Two pointers | Not started
13 |  | Easy | Prefix sum | Not started
13 |  | Easy | Arrays | Not started
13 |  | Easy | Two pointers | Not started
15 |  | Easy | Strings | Not started
15 |  | Easy | Strings | Not started
16 |  | Easy | Two pointers | Not started
16 |  | Easy | Two pointers | Not started
17 |  | Medium | Two pointers | Not started
17 |  | Easy | Two pointers | Not started
18 |  | Easy | Strings | Not started
18 |  | Easy | Sliding window | Not started
19 |  | Medium | Strings | Not started
19 |  | Easy | Two pointers | Not started
20 |  | Medium | Two pointers | Not started
20 |  | Easy | Strings | Not started
20 |  | Easy | Strings | Not started
20 |  | Easy | Strings | Not started
22 |  | Medium | Sliding window | Not started
23 |  | Medium | Sliding window | Not started
23 |  | Medium | Sliding window | Not started
24 |  | Medium | Prefix sum | Not started
25 |  | Easy | Arrays | Not started
25 |  | Medium | Arrays | Not started
26 |  | Easy | Hashing | Not started
27 |  | Medium | Prefix sum | Not started
27 |  | Medium | Sliding window | Not started
27 |  | Medium | Hashing | Not started
27 |  | Medium | Sliding window | Not started
29 |  | Easy | Binary search | Not started
29 |  | Easy | Binary search | Not started
30 |  | Easy | Binary search | Not started
30 |  | Medium | Binary search | Not started
31 |  | Medium | Binary search | Not started
31 |  | Medium | Binary search | Not started
32 |  | Medium | Binary search on answer | Not started
32 |  | Medium | Binary search on answer | Not started
33 |  | Easy | Binary search | Not started
33 |  | Medium | Binary search | Not started
34 |  | Medium | Two pointers | Not started
34 |  | Medium | Sorting | Not started
34 |  | Custom | Sorting | Not started
34 |  | Custom | Sorting | Not started
35 |  | Custom | Sorting | Not started
36 |  | Easy | Linked lists | Not started
36 |  | Easy | Fast & slow | Not started
37 |  | Medium | Linked lists | Not started
37 |  | Easy | Linked lists | Not started
38 |  | Easy | Fast & slow | Not started
38 |  | Easy | Linked lists | Not started
39 |  | Easy | Stack & Queue | Not started
39 |  | Easy | Stack & Queue | Not started
40 |  | Easy | Linked lists | Not started
40 |  | Easy | Stack & Queue | Not started
40 |  | Medium | Stack & Queue | Not started
40 |  | Medium | Linked lists | Not started
41 |  | Medium | Linked lists | Not started
41 |  | Medium | Stack & Queue | Not started
41 |  | Medium | Stack & Queue | Not started
41 |  | Medium | Linked lists | Not started
43 |  | Easy | Recursion | Not started
43 |  | Custom | Recursion | Not started
43 |  | Custom | Recursion | Not started
44 |  | Medium | Recursion | Not started
44 |  | Medium | Backtracking | Not started
45 |  | Medium | Backtracking | Not started
45 |  | Medium | Backtracking | Not started
46 |  | Medium | Backtracking | Not started
46 |  | Medium | Backtracking | Not started
47 |  | Medium | Backtracking | Not started
47 |  | Medium | Backtracking | Not started
48 |  | Medium | Backtracking | Not started
48 |  | Medium | Backtracking | Not started
48 |  | Medium | Backtracking | Not started
48 |  | Medium | Backtracking | Not started
49 |  | Hard | Backtracking | Not started
50 |  | Easy | Trees | Not started
50 |  | Easy | Trees | Not started
50 |  | Easy | Trees | Not started
51 |  | Medium | Trees | Not started
51 |  | Medium | Trees | Not started
52 |  | Medium | BST | Not started
52 |  | Medium | BST | Not started
53 |  | Easy | Trees | Not started
53 |  | Medium | BST | Not started
53 |  | Easy | Trees | Not started
54 |  | Easy | BST | Not started
54 |  | Medium | BST | Not started
54 |  | Easy | Trees | Not started
55 |  | Medium | Trees | Not started
55 |  | Easy | Trees | Not started
55 |  | Medium | Trees | Not started
55 |  | Medium | Trees | Not started
57 |  | Easy | Heaps | Not started
57 |  | Medium | Heaps | Not started
58 |  | Medium | Heaps | Not started
58 |  | Medium | Heaps | Not started
59 |  | Hard | Heaps | Not started
59 |  | Medium | Heaps | Not started
60 |  | Hard | Heaps | Not started
61 |  | Easy | Heaps | Not started
62 |  | Medium | Linked lists | Not started
62 |  | Medium | Heaps | Not started
62 |  | Medium | Heaps | Not started
62 |  | Medium | Heaps | Not started
62 |  | Custom | Heaps | Not started
64 |  | Medium | Graphs | Not started
64 |  | Easy | Graphs | Not started
65 |  | Medium | Graphs | Not started
65 |  | Medium | Graphs | Not started
66 |  | Medium | Graphs | Not started
66 |  | Medium | Graphs | Not started
67 |  | Medium | Graphs | Not started
67 |  | Medium | Graphs | Not started
68 |  | Easy | Graphs | Not started
68 |  | Custom | Graphs | Not started
69 |  | Hard | Graphs | Not started
69 |  | Medium | Graphs | Not started
69 |  | Medium | Graphs | Not started
69 |  | Medium | Graphs | Not started
71 |  | Medium | Topological sort | Not started
72 |  | Medium | Topological sort | Not started
73 |  | Medium | Union-Find | Not started
73 |  | Medium | Union-Find | Not started
73 |  | Custom | Union-Find | Not started
74 |  | Medium | Union-Find | Not started
75 |  | Medium | Topological sort | Not started
76 |  | Medium | Union-Find | Not started
76 |  | Hard | Topological sort | Not started
76 |  | Medium | Topological sort | Not started
76 |  | Medium | Union-Find | Not started
78 |  | Medium | Shortest paths | Not started
79 |  | Medium | Intervals | Not started
79 |  | Medium | Intervals | Not started
80 |  | Medium | Intervals | Not started
80 |  | Medium | Intervals | Not started
80 |  | Medium | Intervals | Not started
81 |  | Medium | Greedy | Not started
81 |  | Medium | Greedy | Not started
82 |  | Medium | Shortest paths | Not started
82 |  | Easy | Intervals | Not started
82 |  | Custom | Greedy | Not started
83 |  | Medium | MST | Not started
83 |  | Medium | Greedy | Not started
83 |  | Medium | Greedy | Not started
83 |  | Medium | Shortest paths | Not started
85 |  | Easy | DP | Not started
85 |  | Easy | DP | Not started
86 |  | Easy | DP | Not started
86 |  | Medium | DP | Not started
86 |  | Medium | DP | Not started
87 |  | Medium | DP | Not started
87 |  | Medium | DP | Not started
88 |  | Medium | DP | Not started
88 |  | Medium | DP | Not started
89 |  | Medium | DP | Not started
90 |  | Medium | DP | Not started
90 |  | Medium | DP | Not started
90 |  | Medium | DP | Not started
92 |  | Medium | DP | Not started
92 |  | Custom | DP | Not started
92 |  | Custom | DP | Not started
93 |  | Medium | DP | Not started
93 |  | Medium | DP | Not started
94 |  | Medium | DP | Not started
94 |  | Medium | DP | Not started
94 |  | Medium | DP | Not started
95 |  | Medium | DP | Not started
95 |  | Medium | DP | Not started
95 |  | Medium | DP | Not started
96 |  | Medium | DP | Not started
97 |  | Medium | DP | Not started
97 |  | Medium | DP | Not started
99 |  | Medium | DP | Not started
100 |  | Medium | DP | Not started
100 |  | Medium | DP | Not started
101 |  | Medium | Greedy | Not started
101 |  | Medium | DP | Not started
102 |  | Medium | DP | Not started
102 |  | Medium | DP | Not started
103 |  | Hard | DP | Not started
106 |  | Easy | Monotonic | Not started
106 |  | Medium | Monotonic | Not started
106 |  | Medium | Monotonic | Not started
107 |  | Hard | Monotonic | Not started
107 |  | Hard | Monotonic | Not started
107 |  | Medium | Monotonic | Not started
108 |  | Medium | Trie | Not started
108 |  | Medium | Trie | Not started
108 |  | Medium | Trie | Not started
109 |  | Easy | Bits & Math | Not started
109 |  | Easy | Bits & Math | Not started
109 |  | Easy | Bits & Math | Not started
109 |  | Easy | Bits & Math | Not started
109 |  | Easy | Bits & Math | Not started
110 |  | Easy | Bits & Math | Not started
110 |  | Medium | Monotonic | Not started
110 |  | Custom | Monotonic | Not started
110 |  | Custom | Bits & Math | Not started
111 |  | Hard | Trie | Not started
111 |  | Medium | Bits & Math | Not started
111 |  | Medium | Bits & Math | Not started
111 |  | Hard | Two pointers | Not started
113 |  | Medium | Sliding window | Not started
113 |  | Hard | Sliding window | Not started
114 |  | Medium | Graphs | Not started
114 |  | Medium | Linked lists | Not started
117 |  | Medium | Trees | Not started
117 |  | Hard | DP | Not started
117 |  | Hard | DP | Not started
117 |  | Medium | Bits & Math | Not started
117 |  | Medium | Two pointers | Not started
117 |  | Hard | Stack & Queue | Not started
117 |  | Hard | Graphs | Not started
117 |  | Medium | DP | Not started
117 |  | Hard | Backtracking | Not started
117 |  | Medium | Trees | Not started
117 |  | Hard | DP | Not started
117 |  | Medium | Sliding window | Not started
117 |  | Medium | Arrays | Not started
117 |  | Custom | Matrix | Not started
117 |  | Custom | Sorting | Not started
117 |  | Custom | Stack & Queue | Not started
117 |  | Custom | Backtracking | Not started
117 |  | Custom | DP | Not started
117 |  | Custom | Trees | Not started
118 |  | Medium | Hashing | Not started
118 |  | Medium | Matrix | Not started
118 |  | Medium | Matrix | Not started
118 |  | Medium | Matrix | Not started
120 |  | Medium | Binary search | Not started
120 |  | Medium | Binary search | Not started
121 |  | Medium | Binary search | Not started
121 |  | Medium | Heaps | Not started
122 |  | Medium | Trees | Not started
122 |  | Medium | Trees | Not started
123 |  | Medium | Trees | Not started
124 |  | Medium | Trees | Not started
125 |  | Medium | Trees | Not started
125 |  | Hard | Linked lists | Not started
127 |  | Hard | Binary search on answer | Not started
128 |  | Hard | Trees | Not started
128 |  | Hard | Trees | Not started
129 |  | Medium | Graphs | Not started
129 |  | Hard | Shortest paths | Not started
130 |  | Hard | Graphs | Not started
132 |  | Hard | Graphs | Not started
132 |  | Medium | Shortest paths | Not started
132 |  | Custom | Shortest paths | Not started
134 |  | Medium | Stack & Queue | Not started
134 |  | Medium | Stack & Queue | Not started
135 |  | Medium | Stack & Queue | Not started
135 |  | Medium | Stack & Queue | Not started
136 |  | Medium | Hashing | Not started
136 |  | Medium | Sliding window | Not started
137 |  | Medium | Prefix sum | Not started
137 |  | Medium | Prefix sum | Not started
138 |  | Hard | Arrays | Not started
139 |  | Easy | Hashing | Not started
139 |  | Medium | Arrays | Not started
139 |  | Medium | Fast & slow | Not started
139 |  | Medium | Arrays | Not started
141 |  | Medium | Fast & slow | Not started
141 |  | Easy | Fast & slow | Not started
142 |  | Medium | Linked lists | Not started
143 |  | Medium | Stack & Queue | Not started
143 |  | Medium | BST | Not started
144 |  | Medium | Graphs | Not started
144 |  | Medium | Graphs | Not started
146 |  | Medium | Binary search | Not started
146 |  | Medium | Heaps | Not started
155 |  | Easy | Strings | Not started
155 |  | Medium | Sorting | Not started
159 |  | Hard | Strings | Not started
165 |  | Hard | Linked lists | Not started
166 |  | Hard | Binary search | Not started
170 |  | Easy | Strings advanced | Not started
170 |  | Custom | Strings advanced | Not started
172 |  | Hard | Strings advanced | Not started
172 |  | Medium | Strings advanced | Not started
173 |  | Hard | Strings advanced | Not started
177 |  | Medium | Range queries | Not started
177 |  | Custom | Range queries | Not started
179 |  | Hard | Range queries | Not started
179 |  | Medium | Intervals | Not started
180 |  | Hard | Heaps | Not started
185 |  | Medium | Trie | Not started
194 |  | Hard | DP | Not started
195 |  | Medium | DP | Not started
195 |  | Hard | DP | Not started
198 |  | Medium | Two pointers | Not started
199 |  | Custom | Shortest paths | Not started
199 |  | Custom | Graphs | Not started
202 |  | Hard | Monotonic | Not started
202 |  | Custom | DP | Not started
209 |  | Hard | Stack & Queue | Not started

## REVIEW
Planned day | Concept (explain aloud) | Learned on | D+1 | D+3 | D+7 | D+14 | D+30 | Last result
1 | Why is reading a[i] O(1) but finding a value O(n)?
2 | What is overflow and when should a sum use long?
3 | What does a variable of a value type hold, and what does a reference-type variable hold?
4 | Where does a struct live — the stack or the heap? (It depends on where it is declared.)
8 | What is boxing, what does it cost, and name three places it happens by accident.
9 | State the Equals/GetHashCode contract and what breaks without it.
10 | Why is Dictionary lookup O(1) on average, and what makes it O(n)?
11 | Explain ref, out and in in one sentence each.
15 | Why is string concatenation in a loop O(n²)?
16 | What is the job of a constructor?
17 | Interface or abstract class — how do you decide?
18 | Why composition over inheritance?
22 | IEnumerable vs IQueryable — why does it matter for a database query?
23 | What is deferred execution and give one bug it causes.
24 | What does a closure allocate, and what is the loop-variable trap?
25 | What is the difference between throw and throw ex?
29 | Why does a finalizer make collection take (at least) two GC cycles?
30 | Why is a gen 0 collection cheap and a gen 2 collection expensive?
31 | What does await actually do?
32 | Why does calling .Result deadlock in an app with a synchronization context?
36 | What is thread-pool starvation and how would you spot it?
37 | What is a race condition at the memory level?
38 | What causes a deadlock and how do you prevent one?
39 | When does Parallel.For hurt rather than help?
43 | .NET Framework vs modern .NET in sixty seconds.
44 | Trace a request from Kestrel to your controller and back.
45 | Explain DI lifetimes and the captive dependency problem.
46 | How does configuration precedence work?
50 | Which HTTP methods are idempotent, and why does it matter?
51 | What is inside a JWT, and what is the difference between signing and encryption?
52 | What is the N+1 problem, how do you find it, and how do you fix it?
53 | Compare cache-aside, write-through and write-behind.
57 | When would you denormalise on purpose?
58 | Why does an index make reads faster and writes slower?
59 | Why can WHERE YEAR(created) = 2026 not use an index?
60 | What is the logical execution order of a SQL statement?
64 | State the four ACID properties and what each protects.
65 | What is write skew, and why does snapshot isolation permit it?
66 | Optimistic or pessimistic locking — when each?
67 | How do you change a schema without downtime?
71 | What happens when you type a URL and press enter? (5-minute version)
72 | Flow control or congestion control — what is the difference?
73 | Explain CORS and preflight (with the corrected middleware order).
74 | Why is a context switch expensive?
78 | Why does async I/O not need a thread while waiting?
79 | Explain the delivery guarantees, and how you get exactly-once *processing*.
80 | SQS, RabbitMQ or Kafka — how do you choose?
81 | What is the outbox pattern and what problem does it solve?
85 | Why can a read replica serve stale data, and how do you hide that from a user?
86 | What does CAP actually say, and what is the common misreading?
87 | Why is Redis being single-threaded a feature?
88 | L4 vs L7 load balancer?
92 | Explain Single Responsibility without reciting the definition.
93 | Why is Dependency Inversion not the same as using a DI container?
94 | Decorator or inheritance?
95 | Why is untestable code usually badly designed code?
99 | Why is 'authenticated' not the same as 'authorized'?
100 | How do you prove tenant isolation rather than assert it?
101 | What is mass assignment and how do DTOs prevent it?
102 | Why is CORS not a CSRF defence?
106 | Why do multi-stage Docker builds matter?
107 | Why is 'localhost' inside a container not your machine?
108 | What does your CI pipeline protect against, stage by stage?
109 | Liveness or readiness — what is the difference and why does it matter?
113 | Why is two-phase commit avoided across services?
114 | Why can a distributed lock not be made safe with timeouts alone?
115 | Choreography or orchestration for a saga?
116 | Explain circuit-breaker states and why retries alone amplify an outage.
120 | What are RED and USE?
121 | What do p50, p95 and p99 tell you, and why not the average?
122 | What does least privilege mean in IAM?
123 | How do you stop one tenant starving the others?
127 | Why separate job acceptance latency from job completion time?
128 | A latency spike with low CPU — what do you check first?
129 | What are RPO and RTO?
130 | Walk me through exactly what happens when a worker dies mid-job.
134 | What are the design steps, in order?
135 | Why are payment systems obsessed with idempotency?
136 | Why does saying 'we' cost you the answer?
137 | How do you answer 'what would you do differently?'
141 | What do you do in the first five minutes of a coding round?
142 | How do you approach a 45-minute LLD from a blank page?
143 | How do you open a system design round?
144 | Why apply to mid-tier companies first?
148 | How do you code with no autocomplete and no compiler?
149 | Where does concurrency appear in a task scheduler?
150 | What separates a passing design from a strong one?
151 | Your English stalls mid-answer. What do you do?
155 | What is the Bar Raiser looking for?
156 | Which states does an ATM have?
157 | How do you keep an LLD extensible?
158 | How do you analyse an interview afterwards?
162 | What does the hiring committee mean for how you answer?
163 | What is the code comprehension round and how do you prepare?
164 | How do two people edit the same paragraph safely?
165 | How do you handle a hot key in a distributed cache?
169 | When does Kafka beat SQS, concretely?
170 | Kafka claims exactly-once semantics. Is that a contradiction?
171 | What is a watermark?
172 | Why is replay a design requirement?
176 | Linearizability or serializability — what is the difference?
177 | Active-active or active-passive?
178 | Why is cardinality the hard part of a metrics system?
179 | How would you fail over your project to another region?
183 | How do you use AI tools, and how do you verify their output?
184 | What is actually hard about building a RAG service?
185 | Why pgvector rather than a dedicated vector database?
186 | How do you evaluate a RAG system?
190 | Why must a RAG system be able to say 'I don't know'?
191 | How do you stop a malicious document from making the model do something?
192 | Tools, resources and prompts in MCP — who controls each?
193 | How do you control the cost of an LLM feature?
197 | Why did you choose this extension for your target roles?
198 | Explain the extension in 2 minutes.
199 | When would you use a trie service vs a search engine?
200 | When is CQRS over-engineering?
204 | Explain the .NET request pipeline end to end.
205 | Explain isolation levels per engine.
206 | What happens when you type a URL?
207 | Explain at-least-once delivery and idempotency.
211 | What will this company's loop test, according to the recruiter?
212 | How do you analyse an interview afterwards?
213 | What do you say when asked for your expected salary?
214 | Why do you want to move to this country? (only if relevant)
218 | What is boxing and when does it happen?
219 | How do you ask for more time to decide?
220 | How does your project behave when the database is down?
221 | What did these eight months change in how you engineer?

## WEAK
Item | Added on | Where it came from | Try 1 | Try 2 | Cleared on | Note

## DESIGNS
ID | Type | Design | Planned day(s) | Done on | Minutes | Score /20 | What I missed | Redo on
url-shortener | HLD |  | 20, 27, 34, 55, 202
pastebin | HLD |  | 117
rate-limiter | HLD |  | 69, 202
notification | HLD |  | 83, 146, 202
job-platform | HLD |  | 76, 167, 216
dropbox | HLD |  | 195
news-feed | HLD |  | 125, 209
ecommerce | HLD |  | 139
payment | HLD |  | 139, 216
chat | HLD |  | 118, 209
web-crawler | HLD |  | 143
youtube | HLD |  | 150, 199
typeahead | HLD |  | 150, 199
google-docs | HLD |  | 164
distributed-cache | HLD |  | 165
ad-click-aggregation | HLD |  | 174
metrics-monitoring | HLD |  | 181
proximity | HLD |  | 188, 199
object-storage | HLD |  | 195
uber | HLD |  | 188
hotel-booking | HLD |  | 132, 216
ticket-booking | HLD |  | 132
flight-booking | HLD |  | 119
restaurant-reservation | HLD |  | 124
food-delivery | HLD |  | 126
logging-pipeline | HLD |  | 131
email-delivery | HLD |  | 133
instagram | HLD |  | 138
tiktok | HLD |  | 140
pinterest | HLD |  | 145
reddit | HLD |  | 147
netflix | HLD |  | 152
spotify | HLD |  | 154
trending-topics | HLD |  | 159
cdn | HLD |  | 161
ad-serving | HLD |  | 166
recommendations | HLD |  | 168
leaderboard | HLD |  | 173
multi-region | HLD |  | 181
id-generator | HLD |  | 175
package-tracking | HLD |  | 158
logger | LLD |  | 41, 42
parking-lot | LLD |  | 48, 55, 153
lru-cache | LLD |  | 62
rate-limiter-lld | LLD |  | 97, 153
splitwise | LLD |  | 90
elevator | LLD |  | 104
seat-reservation | LLD |  | 111
task-scheduler | LLD |  | 149
vending-machine | LLD |  | 142
atm | LLD |  | 156
tic-tac-toe | LLD |  | 180
chess | LLD |  | 182
snake-ladder | LLD |  | 187
library | LLD |  | 157
hotel-booking-lld | LLD |  | 189
notification-lld | LLD |  | 194
pub-sub | LLD |  | 196
file-system | LLD |  | 201
food-delivery-lld | LLD |  | 203
traffic-light | LLD |  | 208
meeting-scheduler | LLD |  | 210
chat-lld | LLD |  | 215
reddit-lld | LLD |  | 217
linkedin-lld | LLD |  | 222
calendar | LLD |  | 224
voting | LLD |  | 117
url-shortener-lld | LLD |  | 119
uber-lld | LLD |  | 124
airline | LLD |  | 126
restaurant | LLD |  | 131
car-rental | LLD |  | 133
order-management | LLD |  | 138
cricbuzz | LLD |  | 140
truecaller | LLD |  | 145
stock-exchange | LLD |  | 147
lms | LLD |  | 152
payment-lld | LLD |  | 154
autocomplete-lld | LLD |  | 159
inventory | LLD |  | 161
feature-flags | LLD |  | 166
snowflake-id | LLD |  | 168
circuit-breaker | LLD |  | 173
retry-backoff | LLD |  | 175
metrics-lld | LLD |  | 180
auth-system | LLD |  | 182
rbac | LLD |  | 187
web-crawler-lld | LLD |  | 189
recommendation-lld | LLD |  | 194
producer-consumer | LLD |  | 196

## STORIES
Story (real only) | From | Worksheet | Recorded | Customer Obsession | Ownership | Invent and Simplify | Are Right, A Lot | Learn and Be Curious | Hire and Develop the Best | Insist on the Highest Standards | Think Big | Bias for Action | Frugality | Earn Trust | Dive Deep | Have Backbone; Disagree and Commit | Deliver Results | Strive to be Earth's Best Employer | Success and Scale Bring Broad Responsibility
Email pipeline: 7–10 h → about 1–1.5 h (flagship) | Casepoint | No | No
Embedding eligibility counts: 11 queries → 2 set-based | Casepoint | No | No
FOIA / regulated disclosure workflows | Casepoint | No | No
Legacy code: tracing paths before changing | Casepoint | No | No
SQL / index tuning on eDiscovery data | Casepoint | No | No
Multilingual processing | Casepoint | No | No
Production incident resolution | Vision Infotech | No | No
Client modules end to end | Vision Infotech | No | No
SignalR + FCM messaging (VCDoctor) | Vision Infotech | No | No
Payments: Stripe / PayPal / CCAvenue | Vision / Zibma | No | No
Vonage video (VCDoctor) | Vision Infotech | No | No
100k+ record performance (ERP) | Zibma Infotech | No | No
ERP reporting / .NET Core APIs into ASP.NET | Zibma Infotech | No | No
Disagreement with a senior — FIND A REAL ONE |  | No | No
Hard feedback / I was wrong — FIND A REAL ONE |  | No | No
Helping a junior — only if real |  | No | No
The job platform project — only after it is built | Study project | No | No

## JOURNAL
Date | One line: problem, decision, outcome | Story candidate?

## PROJECT
Milestone | Week | Build | Acceptance test | Status | Evidence (link / note)
M1 | 11 | Small API, durable metadata, state machine | Job readable after restart; illegal transition rejected | Not started
M2 | 12 | RabbitMQ + worker, attempt history, graceful shutdown | Stopped worker → message redelivered, job finishes | Not started
M3 | 13 | Transactional outbox + relay | Crash between commit and publish → job still delivered | Not started
M4 | 14 | Idempotent consumption and submission | Duplicate delivery → one effect; duplicate POST → same response | Not started
M5 | 15 | Security | 10 security tests pass, incl. cross-tenant 404 | Not started
M6 | 16 | Docker Compose + CI | Clean clone runs; failing test blocks merge | Not started
M7 | 17 | Retries, DLQ/replay, leases/reaper, cancellation | Kill worker mid-job → completes; poison → DLQ → replay | Not started
M8 | 18 | Fairness, observability, deployment | Noisy tenant cannot starve; one job traced end to end | Not started
M9 | 19 | Load tests, failure tests, restore | Benchmark report complete; restore verified | Not started
M10 | 20 | README, decisions, defense, scope freeze | 15-minute defense recorded | Not started
M11 | 25–28 | AI increment (indexing, retrieval, evaluation, optional MCP) | Measured recall@k; negative security tests | Not started
M12 | 29 | Optional: Kubernetes/KEDA or SQS port | Runs, with a written limitation | Not started

## APPLY
Company | Country | Route / note | Tier | On sponsor register? | LinkedIn test | Applied on | Referral | Stage | Next action | By when
Thomson Reuters | Canada | Seeded Aug 2026 — verify route first | 3A
OpenText | Canada | Seeded Aug 2026 — verify | 3A
Magnet Forensics | Canada | Sponsorship unverified | 3A
Constellation Software | Canada | Seeded — verify | 3A
Xero | New Zealand | Seeded — verify | 3B
Datacom | New Zealand | Seeded — verify | 3B
Nuix | Australia | Stack may be Java-leaning — verify | 3C
Objective Corp | Australia | Seeded — verify | 3C
WiseTech | Australia | Seeded — verify | 3C
Microsoft Dublin | Ireland | Ireland gated on NFQ check | 3E
Fidelity | Ireland | Ireland gated on NFQ check | 3E
Version 1 | Ireland | Ireland gated on NFQ check | 3E
ASML | Netherlands | Seeded — verify | 3F
Visma | Nordics | Seeded — verify | 3G
EPAM | Poland | Seeded — verify | 3I
Relativity (Krakow) | Poland | Only company checked with live evidence (Aug 2026); apply at senior level | 3I/3K
Casepoint US (L-1 transfer) | USA | CLOSED — employer offers no overseas transfer | struck

## INTERVIEWS
Company | Round | Date | Questions asked (verbatim) | What went well | What went badly (exact moment) | Root cause | Repair action | Repair by

## DASHBOARD
Measure | Value
Days done (of 224)
Share of days done
Problems solved independently
Problems with a hint
Problems failed / solution read
Concepts passing their last review
Weak items still open
Designs done
Stories recorded
Journal lines
Project milestones done
Applications sent
Interviews analysed